## Project Management Data
[9 empty] | January | 23
Excel Sample Data | [8 empty] | January | 18
[9 empty] | January | 7
Project Management Data | [8 empty] | February
January
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress |  |  | January
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 78% |  |  | February
Marketing | Content Creation | Bob | 2024-01-14 | 14 | 2024-01-28 | 100% |  |  | February
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 45% |  |  | February
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0% |  |  | March
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | 2024-01-20 | 100% |  |  | February
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 78% |  |  | February
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | 2024-02-29 | 0% |  |  | March
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | 2024-02-23 | 100% |  |  | January
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 100% |  |  | January
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0% |  |  | February
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2024-02-24 | 10% | 4 | Marketing | January
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | 2024-02-09 | 78% | 3 | Product Dev | February
Financial | Investment Planning | Mark | 2024-03-19 | 25 | 2024-04-13 | 100% | 3 | Customer Svc | March
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | 2024-01-25 | 50% | 3 | Financial | January
Research | Data Collection | Olivia | 2024-01-26 | 32 | 2024-02-27 | 0% | 3 | Research | February
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | 2024-03-26 | 0% | 3 | Development | March
Development | Software Development | Quinn | 2024-01-02 | 36 | 2024-02-07 | 100% | 3 | Production | January
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | 2024-03-13 | 0% | 3 | Sales | January
Development | Code Review | Sam | 2024-03-14 | 30 | 2024-04-13 | 0% | 3 | Support | February
Production | Manufacturing | Tim | 2024-01-03 | 47 | 2024-02-19 | 30% | 3 | Operations | January
Production | Quality Control | Ursula | 2024-02-17 | 27 | 2024-03-15 | 0% | 3 | Cunsultiing | January
Production | Packaging Design | Victor | 2024-03-14 | 22 | 2024-04-05 | 0% | 3 | Training | March
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | 2024-03-03 | 70% | 3 | Events | January
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | 2024-01-26 | 78% | 3 | Logistics | February
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | 2024-03-09 | 0% | 3 | Engeenering | February
Support | Technical Support | Zoe | 2024-01-01 | 25 | 2024-01-26 | 100% |  |  | January
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | 2024-02-27 | 100% |  |  | February
Support | Software Updates | Bella | 2024-03-02 | 22 | 2024-03-24 | 0% |  |  | March
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | 2024-02-02 | 40% |  |  | January
Operations | Inventory Management | Diane | 2024-02-03 | 25 | 2024-02-28 | 0% |  |  | January
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | 2024-03-20 | 0% |  |  | February
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | 2024-02-06 | 60% |  |  | January
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-03-05 | 0% |  |  | February
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | 2024-03-31 | 0% |  |  | February
Training | Employee Training | Isaac | 2024-01-04 | 27 | 2024-01-31 | 80% |  |  | January
Training | Certification Programs | Jane | 2024-01-28 | 30 | 2024-02-27 | 0% |  |  | January
Training | Skill Development | Kyle | 2024-02-28 | 22 | 2024-03-21 | 0% |  |  | March
Events | Event Planning | Laura | 2024-01-03 | 25 | 2024-01-28 | 30% |  |  | January
Events | Conference Management | Mike | 2024-02-03 | 20 | 2024-02-23 | 0% |  |  | February
Events | Sponsorship Coordinatio | n Nancy | 2024-02-24 | 35 | 2024-03-30 | 0% |  |  | February
Logistics | Supply Chain Management | Oscar | 2024-01-03 | 25 | 2024-01-28 | 50% |  |  | January
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | 2024-02-28 | 100% |  |  | January
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | 2024-04-18 | 0%
Engineering | Product Design | Rachel | 2024-01-02 | 25 | 2024-01-27 | 20%
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2024-02-24 | 0%
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | 2024-03-21 | 0%
[5 empty] | January | 16
[5 empty] | January | 17
[5 empty] | February | 15
[5 empty] | March | 5
January
January
February
February
March
April
February
February
April
January
February
March
February
March
April
February
March
April
March
January
March
January
February
March
February
February
March
February
March
March
January
February
March
January
February
March
January
February
April
January
February
March
January
January
January
February
March
January
January

## Sheet1
Project Management Data Of The first Quarter Of a B to B FMCG Company